Transmittal: Mummy Portraits of Roman Egypt, Volume 2: Emerging Research from the APPEAR Project

Book team: Rachel Barth, Greg Albers, Erin Dunigan, Jenny Park, Jeffrey Cohen, Victoria Gallina, Danielle Brink

Transmittal: March 17, 2025

Book season: Fall 2025

Inventory of book files

| Number of element in transmittal folder | Title | Author | Status |
| --- | --- | --- | --- |
| 00a | Half title and title page |  | TR |
| 00b | copyright page |  | TR |
| 00c | TOC |  | TR |
| 1 | Foreword | Tim Potts | IP—expected to be final within a few weeks |
| 2 | Introduction | Svoboda and Cartwright | TR |
| 3 | [paper 1] | Van Daal | TR |
| 4 | [paper 2] | Brunel-Duverger et al. | IP—I just got this from the copy editor today and am working on finalizing it now. |
| 5 | [paper 3] | Brøns et al. | IP—expected to be final within a week or so |
| 6 | [paper 4] | Mastandrea et al. | TR |
| 7 | [paper 5] | Tsakri and Panagakos | TR |
| 8 | [paper 6] | Rogge and Cartwright | TR |
| 9 | [paper 7] | Cartwright | TR |
| 10 | [paper 8] | Svoboda et al. | TR |
| 11 | [paper 9] | Mazurek and Spaabæk | TR |
| 12 | [paper 10] | Thistlewood | TR |
| 13 | [paper 11] | Van Oppen de Ruiter | TR |
| 14 | [paper 12] | Mahon et al. | IP—expected to be final within a week or so |
| 15 | [paper 13] | Verri et al. | IP—returned to the copy editor from authors, expected to be finalized this week |
| 16 | [paper 14] | Spence and Twilley | TR |
| 17 | [paper 15] | Bisulca et al. | TR |
| 18 | [paper 16] | Kijowska et al. | TR |
| 19 | [paper 17] | Smith et al. | TR |
| 20 | Glossary |  | TR |
| 21 | Bibliography |  | TR—some lingering issues, but I will address these by first pages |
| 22 | APPEAR Participants (institutions) |  | TR |
| 23 | Contributors |  | TR |
| 24 | Acknowledgments |  | IP—expected to be final by first pages |
| 25 | Master captions list |  | TR, just missing the captions from papers 3, 12, and 13 |

Editorial notes

About this book: This volume presents the latest cutting-edge research on mummy portraits and shrouds from Roman Egypt. These papers were presented at the second APPEAR conference, held in 2022. The authors of the papers were asked to provide us with hi-res, publication-ready photography and all the rights to reproduce images.

Marie Svoboda (Villa curator) and Caroline Cartwright (scientist at the British Museum) are the volume editors for this book. All communications should go between me and them, unless otherwise arranged (i.e. Danielle has direct communication for rights documents and image questions). This is for the purpose of streamlining communication, not for cutting anyone out of communication with the volume editors. Please let me know anytime you would like to convene a meeting with the volume editors. Marie’s email is MSvoboda@getty.edu.

I have set team check-in meetings moving forward. If anyone cannot come to a future meeting, please just let me know and I will determine whether to cancel the meeting, record it, or get you information afterward. We can designate one of those meetings as a layout meeting with Marie and Caroline, if digital wants to have one. (For layout, we can also elect to simply send a PDF and link to the site to Marie and Caroline, with review instructions—this is because this book will be modeled on and have the same look at APPEAR 1, for which they were also the volume editors.)

I hope to finalize all remaining papers in this week within a week or so. The foreword and the acknowledgments will be final by the time of first pages at the latest.

A PDF of the setting copy will be on the server once all papers are finalized.

Note about figure 16.10 in captions document: this caption has a graphic in it. The authors prefer this caption, but if Quire can’t accommodate that, they’ve supplied me with a text-only alternative caption.

This is the caption:

Schematic visualization of the XRF results with thirty-four measurement spots. The dimensions of the spots are shown against the size of the entire object. Recorded spectra are presented in the form of a colorful matrix. The scale () reflects the relative variation in the intensity of the signals from the lowest (white) to the highest (red). In all analyzed spots, the signals of two elements were observed: iron (Fe, lines Kα, and K) and lead (Pb, lines Lα, Lβ, Lγ, and M). Such elemental information is consistent with the presence of lead white pigment. Bright green dots over the portrait indicate spots of FTIR.

In the captions document, all alt text fields say TK. I will follow up with Nola on the plan for alt text for this book.

Digital notes (Erin, Greg, Jenny, Alex)

Do we want to have a Zoom layout meeting with Marie and Caroline, or instead give them a review period?

I am getting instructions from Marie as to which images, if any, need to be layered. I don’t think it’s very many. She is having surgery later this week and won’t be able to give me this immediately, but I’ve asked her for these instructions within a week or two, max.

Anything else to discuss from Digital?

Design and production notes (Jeffrey, Tori)

-Jeffrey created cover draft, approved by Marketing

Anything else to discuss from a design and production standpoint?

Rights update and notes (Danielle)

For this book, all authors were contractually obligated to provide us with publication-ready images and the permission to reproduce them. Danielle can update on the images, but I think they are largely ok—some are small, but this is the nature of conservation images. The authors largely did not give us adequate permission to publish the images, so Danielle has been working hard on that with Marie.

This is the status of the permissions:

Marie’s responses are below in brown(?) and Danielle’s are highlighted. She’s already sent out most of the forms so now we are just waiting to receive them.

- Paper #4 – Mastandrea: Perms TK. – form sent and waiting to receive

- Paper #5 - Tsakri and Panagakos: Perms TK. sent and waiting

- Paper #7 – Cartwright: Perms TK. Will send forms to Caroline Cartwright.

- Paper #9 - Mazurek and Spaabaek: Perms not required but do let me know if these should be credited to the contributor. I will ask Mazurek

- Paper #10 – Thistlewood: Perms TK. Still to send

- Paper #11: van Oppen: Perms TK from Martin van Wagner Museum, Pushkin Museum of Fine Art, Harvard Art Museums, Rosicrucian Egyptian Museum, Smith College Museum of Art, University of Zurich (Universität Zürich) Museum and Collections, British Museum (Danielle, I believe you are contacting them for higher res. images and permission?), Yale University Art Gallery, Rijksmuseum van Oudheden, Freud Museum, Kunsthistorisches Museum Wien, Staatliche Museen zu Berlin, Jevon Thistlewood, Spanish National Research Council, Museo Archeologico Nazionale di Napoli, and Phoebe A. Hearst Museum of Anthropology (UC Berkeley). I am waiting for the higher res files and license for figs. 11.3g and 11.4g from the BM.

- Paper #13 - Verri et, al: Perms TK. Sent and waiting. Verri will also have a few new image files in his book—there are no FPOs for these technical images yet. We should have the additional files, and the final Verri paper soon.

- Paper #14 – Spence and Twilley: Perms TK. Sent and waiting

- Paper #15 - Bisulca, Hanspach-Bernal, and Steel: No perms required for works as images are in the PD and free to use according to the Walters and Detroit Institute website, but perms may be required for the technical images if photographer owns copyright. I will inquire

- Paper #16 – Kijowska et al.: Perms TK sent and waiting

- Paper #17 – Smith et al.: Perms TK. Still to send